## Sheet1
Total Hours Spent
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | [8 empty] | Plan
ckc2 | 5 | 7 | 7 | 12 | 8 | 7 | 8
cts12 | 2 | 6 | 5 | 6 | 8 | 6 | 9 | [8 empty] | Date | Feature
gwh18 | 8 | 8 | 6 | 11 | 7 | 11 | 13 | [8 empty] | 2023-04-16 | Front-end and Backend finished and ready for docking
jat92 | 7 | 8 | 8 | 7 | 7 | 8 | 6 | [8 empty] | 2023-04-23 | Back and front need to be at least partially integrated
jib16 | 5 | 7 | 7 | 10 | 8 | 8 | 9 | [8 empty] | 2023-04-23 | Junit package 90% done
seh25 | 7 | 4 | 7 | 9 | 8 | 8 | 7 | [8 empty] | 2023-04-23 | Design Specification feedback resolved
shr27 | 8 | 8 | 12 | 10 | 16 | 7 | 12 | [8 empty] | 2023-04-28 | There needs to be partial implementation reviewed and submitted to src
tyw1 | 10 | 10 | 16 | 9 | 8 | 6 | 10 | [8 empty] | 2023-05-02 | Shit hits the fan
Total | 52 | 58 | 68 | 74 | 70 | 61 | 74 | [8 empty] | 2023-05-05 | Celebratory drink(or cry)
[16 empty] | 2023-05-05 | Code must be submitted
Total Hours spent per member | [15 empty] | 2023-05-07 | Maintenance manual needs to be made | bar: Total Hours Spent Week 1 to Total Hours Spent Week 2
ckc2 | Total Hours Spent Week 1: 54 | [8 empty] | 2023-05-07 | Any additions to documentation have to be done starting this week
ctc12 | Total Hours Spent Week 1: 42 | [8 empty] | 2023-05-09 | Acceptance tests with client will begin sometime over the next 3 days
gwh18 | Total Hours Spent Week 1: 64 | [8 empty] | 2023-05-12 | Final submission of documents
jat92 | Total Hours Spent Week 1: 51 | [8 empty] | 2023-05-12 | Second celebratory drink(or sob)
jib16 | Total Hours Spent Week 1: 54
seh25 | Total Hours Spent Week 1: 50
shr27 | Total Hours Spent Week 1: 73
tyw1 | Total Hours Spent Week 1: 69 |  |  |  | Time Spent on UI Specification
Total | Total Hours Spent Week 1: 457 |  |  |  |  | Week 1 | Week 2 | Week 3 | Week 4
[11 empty] | seh25 | 3 | 2 | 4 | 0
[11 empty] | tyw1 | 3 | 4 | 12 | 8
Time Spent on Test Specification | [10 empty] | jat92 | 0 | 0 | 3 | 4 | bar: Total Hours Spent Week 1 to Total Hours Spent Week 5
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 7 |  |  |  |  | Total | 6 | 6 | 19 | 12
jib16 | 2 | 5 | 4 | 6 | 4
ckc2 | 3 | 6 | 5 | 6 | 3 | 1 |  |  | Time Spent on Backend
Tyw | 0 | 0 | 0 | 0 | 2 |  |  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Total | 5 | 11 | 9 | 12 | 7 | 1 |  |  | shr27 | 2 | 7 | 11 | 8 | 13 | 2
[9 empty] | jat92 | 0 | 0 | 0 | 0 | 0 | 6
[9 empty] | Total | 2 | 7 | 11 | 8 | 13 | 8
Time Spent on Junit Testing
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 |  | Time Spent on Frontend
ckc2 | 0 | 0 | 1 | 2 | 3 | 5 | 4 |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
jib16 | 0 | 0 | 0 | 2 | 1 | 6 | 6 |  | cts12 | 0 | 5 | 5 | 4 | 4 | 3 | 4
seh25 | 0 | 0 | 0 | 6 | 5 | 5 | 4 |  | gwh18 | 4 | 4 | 5 | 8 | 2 | 4 | 0
Total | 0 | 0 | 1 | 10 | 9 | 16 | 14 |  | Total | 4 | 9 | 10 | 12 | 6 | 7 | 4
Total Hours Spent Per Task | Week 4: Design Specification
UI Spec | 43 |  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
Test Spec | 44 |  |  | gwh18 | 2 | 0 | 0 | 0 | 2 | 3 | 8
Des Spec | 24 |  |  | shr27 | 5 | 0 | 0 | 0 | 0 | 3 | 9
Frontend | 48 |  |  | jat92 | 4 | 0 | 0 | 0 | 1 | 0 | 1
Backen | 49 |  |  | Tyw1 | 0 | 0 | 0 | 0 | 2 | 2 | 5
Junit | 36 |  |  | Total | 11 | 0 | 0 | 0 | 5 | 8 | 23