## Sheet1
Total Hours Spent
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
ckc2 | 5 | 7 | 7 | 12 | 8 | 7
cts12 | 2 | 6 | 5 | 6 | 8
gwh18 | 8 | 8 | 6 | 11 | 7 | 11
jat92 | 7 | 8 | 8 | 7 | 7 | 8
jib16 | 5 | 7 | 7 | 10 | 8 | 8
seh25 | 7 | 4 | 7 | 9 | 8 | 8
shr27 | 8 | 8 | 12 | 10 | 16 | 7
tyw1 | 10 | 10 | 16 | 9 | 8 | 6
Total | 52 | 58 | 68 | 74 | 70 | 55
Total Hours spent per member | bar: Total Hours Spent Week 1 to Total Hours Spent Week 2
ckc2 | Total Hours Spent Week 1: 46
ctc12 | Total Hours Spent Week 1: 27
gwh18 | Total Hours Spent Week 1: 51
jat92 | Total Hours Spent Week 1: 45
jib16 | Total Hours Spent Week 1: 45
seh25 | Total Hours Spent Week 1: 43
shr27 | Total Hours Spent Week 1: 61
tyw1 | Total Hours Spent Week 1: 59 |  | Time Spent on UI Specification
Total | Total Hours Spent Week 1: 377 |  |  | Week 1 | Week 2 | Week 3 | Week 4
[8 empty] | seh25 | 3 | 2 | 4 | 0
[8 empty] | tyw1 | 3 | 4 | 12 | 8
Time Spent on Test Specification | [7 empty] | jat92 | 0 | 0 | 3 | 4 | bar: Total Hours Spent Week 1 to Total Hours Spent Week 5
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 |  |  | Total | 6 | 6 | 19 | 12
jib16 | 2 | 5 | 4 | 6 | 4
ckc2 | 3 | 6 | 5 | 6 | 3 |  |  | Time Spent on Backend
Tyw | 0 | 0 | 0 | 0 | 2 |  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Total | 5 | 11 | 9 | 12 | 7 |  |  | shr27 | 2 | 7 | 11 | 8 | 13 | 2
[8 empty] | jat92 | 0 | 0 | 0 | 0 | 0 | 6
[8 empty] | Total | 2 | 7 | 11 | 8 | 13 | 8
Time Spent on Junit Testing
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 |  | Time Spent on Frontend
ckc2 | 0 | 0 | 1 | 2 | 3 | 5 |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
jib16 | 0 | 0 | 0 | 2 | 1 | 6 |  | cts12 | 0 | 5 | 5 | 4 | 4 | 0
seh25 | 0 | 0 | 0 | 6 | 5 | 5 |  | gwh18 | 4 | 4 | 5 | 8 | 2 | 4
Total | 0 | 0 | 1 | 10 | 9 | 16 |  | Total | 4 | 9 | 10 | 12 | 6 | 4
Total Hours Spent Per Task | Week 4: Design Specification
UI Spec | 43 |  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Test Spec | 44 |  |  | gwh18 | 2 | 0 | 0 | 0 | 2 | 3
Des Spec | 24 |  |  | shr27 | 5 | 0 | 0 | 0 | 0 | 3
Frontend | 45 |  |  | jat92 | 4 | 0 | 0 | 0 | 1 | 0
Backen | 49 |  |  | Tyw1 | 0 | 0 | 0 | 0 | 2 | 2
Junit | 36 |  |  | Total | 11 | 0 | 0 | 0 | 5 | 8